## Sheet1
ToppersLectureNotes.com
NO.TASK
| TASK | START DATE | DAYS TO COMPITE
Task 1
Task2 | Find defination related to society and more detail about project | 2017-12-27 | 10
Task 3 | Find another system related to us and find similar tools from them | 2018-01-06 | 11
Task 4 | Get review from user and to ask them what they want from the | 2018-01-17 | 7
Task 5 | list out main feature of system and what are the requirement | 2018-01-24 | 11
Task 6 | calculate analysis,feasibility study and requirements elicitation | 2018-01-27 | 15
Task 7 | web map and user story board | 2018-02-11 | 7
Task 8 | UML diagram | 2018-02-18 | 6
Task 9 | dividing work between group member | 2018-02-25 | 9
Task 10 | work on wireframe | 2018-03-06 | 12
Task 11 | coding | 2018-03-19 | 25
Task 12 | configuration and debugging | 2018-04-14 | 7
Task 13 | testing | 2018-04-22 | 9
| outcome of usability evalution | 2018-05-01 | 6
43096